## Murphy
S/N | Tasks | Project | Duration | Start | Finish | Actual Finish | Status | Comments
1 | Front-end UI simulation of command features | LMS v3 | 4 | 2021-01-04 | 2021-01-07 | 2021-01-06
2 | Front-end UI simulation of groups/zones | LMS v3 | 3 | 2021-01-08 | 2021-01-12 | 2021-01-06
3 | Front-end UI simulation of trigger group/table | LMS v3 | 1 | 2021-01-07 | 2021-01-07 | 2021-01-07
4 | Identification of groups/zones/triggers | LMS v3 | 4 | 2021-01-08 | 2021-01-13 | 2021-01-11
5 | Documentation for JSON data | LMS v3 | 1 | 2021-01-14 | 2021-01-14 | 2021-01-12
6 | MQTT payloads from frontend | LMS v3 | 2 | 2021-01-14 | 2021-01-15 | 2021-01-14
7 | Setup MQTT broker on AWS instance | LMS v3 | 2 | 2021-01-14 | 2021-01-15 | 2021-01-15
8 | Payload structure definition | LMS v3 | 4 | 2021-01-19 | 2021-01-22 |  | Waiting for individual config payloads
9 | Front-end: Login/Signup page | LMS v3 | 3 | 2021-01-25 | 2021-01-27 | 2021-01-27
10 | Front-end: Dashboard main page | LMS v3 | 5 | 2021-01-28 | 2021-02-03 | 2021-02-03
11 | Front-end: Dashboard view | LMS v3 | 5 | 2021-02-04 | 2021-02-10 | 2021-02-18
12 | Front-end: Config | LMS v3 | 7 | 2021-02-19 | 2021-03-03 | 2021-03-02
13 | Front-end: User management/Settings | LMS v3 | 6 | 2021-03-04 | 2021-03-12 | 2021-03-05
14 | Front-end: Photosensor | LMS v3 | 3 | 2021-03-15 | 2021-03-17 | 2021-03-09
15 | Front-end: Edit profile | LMS v3 | 3 | 2021-03-10 | 2021-03-12 | 2021-03-10 |  | Re-estimated start/finish
16 | Front-end: Data charts | LMS v3 | 5 | 2021-03-11 | 2021-03-17 |  | Have to clarify with Viola on the layout of this page
17 | Front-end: Dark mode toggle | LMS v3 | 5 |  |  |  |  | The design for dark mode only includes the dashboard page, might have to wait for more resources.
18 | Documentation for existing/planned features | LMS v3 | 2 |  |  |  | Put on hold till other tasks are done
10 | Front-end: Integrate Threejs scene | LMS v3 | 6 |  |  |  | Implement existing pages first as discussed with Sanjay