## Murphy
S/N | Tasks | Project | Duration | Start | Finish | Actual Finish | Status | Comments
1 | Front-end UI simulation of command features | LMS v3 | 4 | 2021-01-04 | 2021-01-07 | 2021-01-06
2 | Front-end UI simulation of groups/zones | LMS v3 | 3 | 2021-01-08 | 2021-01-12 | 2021-01-06
3 | Front-end UI simulation of trigger group/table | LMS v3 | 1 | 2021-01-07 | 2021-01-07 | 2021-01-07
4 | Identification of groups/zones/triggers | LMS v3 | 4 | 2021-01-08 | 2021-01-13 | 2021-01-11
5 | Documentation for JSON data | LMS v3 | 1 | 2021-01-14 | 2021-01-14 | 2021-01-12
6 | MQTT payloads from frontend | LMS v3 | 2 | 2021-01-14 | 2021-01-15 | 2021-01-14
7 | Setup MQTT broker on AWS instance | LMS v3 | 2 | 2021-01-14 | 2021-01-15 | 2021-01-15
8 | Payload structure definition | LMS v3 | 4 | 2021-01-19 | 2021-01-22 |  | Waiting for individual config payloads
9 | Front-end: Login/Signup page | LMS v3 | 3 | 2021-01-25 | 2021-01-27 | 2021-01-27 | Navigation and layout is done, lacking actual logging in functionality
10 | Front-end: Dashboard main page | LMS v3 | 5 | 2021-01-28 | 2021-02-03 | 2021-02-03
11 | Front-end: Dashboard view | LMS v3 | 5 | 2021-02-04 | 2021-02-10 |  | Dashboard took much longer to implement than expected, but will be completed latest by 22 Feb. Would have to re-estimate the schedule for subsequent tasks based on this.
12 | Front-end: Config | LMS v3 | 7 | 2021-02-19 | 2021-03-03
13 | Front-end: User management/Settings | LMS v3 | 5 | 2021-03-04 | 2021-03-11 |  |  | On leave on 5/3/2021
14 | Front-end: Dark mode toggle | LMS v3 | 5 | 2021-03-12 | 2021-03-18
15 | Documentation for existing/planned features | LMS v3 | 2 |  |  |  | Put on hold till other tasks are done
16 | Front-end: Integrate Threejs scene | LMS v3 | 6 |  |  |  | Implement existing pages first as discussed with Sanjay