## Murphy
S/N | Tasks | Project | Duration | Start | Finish | Actual Finish | Status | Comments
1 | Front-end UI simulation of command features | LMS v3 | 4 | 2021-01-04 | 2021-01-07 | 2021-01-06
2 | Front-end UI simulation of groups/zones | LMS v3 | 3 | 2021-01-08 | 2021-01-12 | 2021-01-06
3 | Front-end UI simulation of trigger group/table | LMS v3 | 1 | 2021-01-07 | 2021-01-07 | 2021-01-07
4 | Identification of groups/zones/triggers | LMS v3 | 4 | 2021-01-08 | 2021-01-13 | 2021-01-11
5 | Documentation for JSON data | LMS v3 | 1 | 2021-01-14 | 2021-01-14 | 2021-01-12
6 | MQTT payloads from frontend | LMS v3 | 2 | 2021-01-14 | 2021-01-15 | 2021-01-14
7 | Setup MQTT broker on AWS instance | LMS v3 | 2 | 2021-01-14 | 2021-01-15 | 2021-01-15
8 | Payload structure definition | LMS v3 | 4 | 2021-01-19 | 2021-01-22 |  | Waiting for individual config payloads
9 | Front-end: Login/Signup page | LMS v3 | 3 | 2021-01-25 | 2021-01-27 | 2021-01-27
10 | Front-end: Dashboard main page | LMS v3 | 5 | 2021-01-28 | 2021-02-03 | 2021-02-03
11 | Front-end: Dashboard view | LMS v3 | 5 | 2021-02-04 | 2021-02-10 | 2021-02-18
12 | Front-end: Config | LMS v3 | 7 | 2021-02-19 | 2021-03-03 | 2021-03-02
13 | Front-end: User management/Settings | LMS v3 | 6 | 2021-03-04 | 2021-03-12 | 2021-03-05
14 | Front-end: Photosensor | LMS v3 | 3 | 2021-03-15 | 2021-03-17 | 2021-03-09
15 | Front-end: Edit profile | LMS v3 | 3 | 2021-03-10 | 2021-03-12 | 2021-03-10
16 | Front-end: Data charts | LMS v3 | 5 | 2021-03-11 | 2021-03-17 | 2021-03-15
17 | Front-end: Relocation pop-up | LMS v3 | 2 | 2021-03-16 | 2021-03-17 | 2021-03-17
18 | Code refactoring | LMS v3 | 8 | 2021-03-18 | 2021-03-29 | 2021-03-29
19 | Front-end: Dashboard view data management | LMS v3 | 3 | 2021-03-30 | 2021-04-01 | 2021-04-01
20 | Front-end: Integrate Threejs scene (not feature complete) | LMS v3 | 10 | 2021-04-05 | 2021-04-16 | 2021-04-15 | Completed: - camera controls - saving to and loading from json (loading broken on github for now) - placing and removing objects in the scene - outline effect on hover and select - multiselect - edit light name - toggle on/off/normal (works with multiselect) - edit group id - edit group colours - select by group id - light name overlay on screen (toggleable) - adding/removing triggers
21 | Front-end: Threejs scene - Selection box | LMS v3 | 2 | 2021-04-19 | 2021-04-20 | 2021-04-16
22 | Front-end: Threejs scene - Groups | LMS v3 | 2 | 2021-04-21 | 2021-04-22 | 2021-04-20
23 | Front-end: Threejs scene - Colour grouping | LMS v3 | 3 | 2021-04-23 | 2021-04-27 | 2021-04-22
24 | Front-end: Threejs scene - Triggers | LMS v3 | 2 | 2021-04-28 | 2021-04-29 | 2021-04-27
25 | Front-end: Documentation and refactoring | LMS v3 | 6 | 2021-04-28 | 2021-05-05 |  | Delayed as I worked on integrating with the backend API first Redux implemented into the general part of the app, currently working on using it with the three.js scene
26 | Front-end: Integrating with backend API | LMS v3 | 6 | 2021-04-28 | 2021-05-05 | 2021-05-05 | Current data used from API (connected locally with docker) - list of areas - list of blocks (per area) - list of lights (per block) - status of light (on/off/dimmed) - fault status of light Time estimate is for the current data available in the backend API
| Front-end: Dark mode toggle | LMS v3 | [5 empty] | The design for dark mode only includes the dashboard page, might have to wait for more resources.
| Documentation for existing/planned features | LMS v3 |  |  |  |  | Put on hold till other tasks are done